## Ark1
Lofthus Frukt & Saft PM: Fredrik Eriksen w/team | START-UP & PLAN |  |  |  |  | SYSTEM DEVELOPMENT |  |  |  |  | BUILD & CODE |  |  |  |  | DESIGN |  |  |  |  | LAUNCH
Start-up date: 08.10.18 | OCTOBER 8 | OCTOBER 9 | OCTOBER 10 | OCTOBER 11 | OCTOBER 12 | OCTOBER 15 | OCTOBER 16 | OCTOBER 17 | OCTOBER 18 | OCTOBER 19 | OCTOBER 22 | OCTOBER 23 | OCTOBER 24 | OCTOBER 25 | OCTOBER 26 | OCTOBER 29 | OCTOBER 30 | OCTOBER 31 | NOVEMBERR 1 | NOVEMBERR 2 | NOVEMBERR 5 | NOVEMBERR 6 | NOVEMBERR 7 | NOVEMBERR 8 | NOVEMBERR 9
End date: 09.11.18 | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | DAY 6 | DAY 7 | DAY 8 | DAY 9 | DAY 10 | DAY 11 | DAY 12 | DAY 13 | DAY 14 | DAY 15 | DAY 16 | DAY 17 | DAY 18 | DAY 19 | DAY 20 | DAY 21 | DAY 22 | DAY 23 | DAY 24 | DAY 25
PROJECT MANAGER | PROJECT MANAGEMENT, OFFER AND AGREEMENT |  |  |  |  | PROJECT MANAGEMENT, CUSTOMER CONTACT |  |  |  |  | PROJECT MANAGEMENT, CUSTOMER CONTACT |  |  |  |  | PROJECT MANAGEMENT, CUSTOMER CONTACT |  |  |  |  | PROJECT MANAGEMENT, CUSTOMER CONTACT
FULL TEAM | TEAM MEETING PRESENT PROJECT
PROJECT MANAGER |  | STRATEGIC PLANNING
PROJECT MANAGER UX DESIGNER |  |  | RESEARCH DETERMINE BRAND STRATEGY
DESIGNER |  |  |  | CREATE STYLE TILES EVALUATE WITH CUSTOMER
BACK-END DEVELOPER FRONT-END DEVELOPER | [5 empty] | Choose: WEB HOST URL NAME AND TOP-LEVEL DOMAIN |  |  | IMPLEMENT PLATFORM ON WEBPAGE BUILD FRAMEWORK
BACK-END DEVELOPER | [6 empty] | Setup: CRM/PLATFORM
BACK-END DEVELOPER PROJECT MANAGER | [7 empty] | DEVELOP BASIC LOGIC FOR SITE FUNCTIONALITY DISCUSS SHIPPING AND PAYMENT PROVIDERS
FULL TEAM | [9 empty] | UPDATE STATUS TEAM MEETING
FRONT-END DEVELOPER | [11 empty] | HTML & CSS CODING
FRONT-END DEVELOPER BACK-END DEVELOPER | [12 empty] | SITE BUILD & INTEGRATION | [8 empty] | CROSS DEVICE, PLATFORM & BROWSER TESTING
UX DESIGNER | [13 empty] | MAKE UX/UI FRIENDLY | [6 empty] | UX/UI TESTING
DESIGNER | [15 empty] | DESIGN BANNERS & ADVERTISEMENT
PHOTOGRAPHER | [15 empty] | PHOTOSHOOT PRODUCTS & STAFF
FRONT-END DEVELOPER UX DESIGNER | [16 empty] | DETERMINE BREAKPOINTS WIREFRAME
DESIGNER | [18 empty] | MAKE IDENTITY ELEMENTS
FRONT-END DEVELOPER | [18 empty] | DESIGN & PUBLISH ARTICLES |  |  |  | VALIDATE
FULL TEAM | [19 empty] | TEAM MEETING REVIEW
FRONT-END DEVELOPER BACK-END DEVELOPER UX DESIGNER | [22 empty] | ALL FUNCTIONALITY TESTING
PROJECT MANAGER BACK-END DEVELOPER FRONT-END DEVELOPER | [23 empty] | ADJUSTMENTS LAST REFINEMENT
FULL TEAM | [24 empty] | LAUNCH